## Cover
SYSTEM TEST REPORT DOCUMENT
Project Name | GoalZone |  |  | Creator | Nguyen Hong Nhung
Project Code | GoalZone |  |  | Issue Date | 2025-03-24
Document Code | GoalZone_System_v1.0 |  |  | Version | 1
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
2025-03-24 | 1.0 |  | A | Create System Test
2025-03-24 | 1.0 | Test report, test case list | A,M | Add function code
2025-03-25 | 1.0 | Test report, test case list | A,M | Add function code

## Test Cases
TEST CASE LIST
Project Name |  | GoalZone
Project Code |  | GoalZone
Test Environment Setup Description |  | 1. Database SQL Server 2. Browser (Chrome, Edge, FireFox, CocCoc) 3. Window 10, 11
No | Function Name | Sheet Name | Description | Pre-Condition
1 | Authentication | Authentication
2 | Main flow of Admin Management | Main flow of Admin Management
3 | Main flow of Staff Management | Main flow of Teacher Management
4 | Main flow of Customer Management | Main flow of Student Management

## Test Report
TEST REPORT
Project Name | GoalZone |  | Creator |  |  | NhungNH
Project Code | GoalZone |  | Reviewer/Approver
Document Code | GoalZone_Test Report_v1.0 |  | Issue Date
Notes | Each iteration has its own statistic for better management
No | Module code | Passed | Failed | Pending | N/A | Number of test cases
1 | Authentication | 24 | 0 | 0 | 0 | 24
2 | Main flow of Admin Management | 22 | 0 | 0 | 0 | 22
3 | Main flow of Staff Management | 39 | 0 | 0 | 0 | 39
4 | Main flow of Customer Management | 41 | 0 | 0 | 0 | 41
| Sub total | 126 | 0 | 0 | 0 | 126
| Test coverage |  | 100 | %
| Test successful coverage |  | 100 | %

## Authenticate
Feature | Authentication | [13 empty] | Passed
Number of TCs | 24 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | Failed
Round 1 | 23 | 1 | 0 | 0
Round 2 | 24 | 0 | 0 | 0
Round 3 | 24 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Register
[Authent - 1] | Test registration with valid input : - UserName - FullName - Password - Re-Password - Phone - Gender - Email - Birthdate | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Guest user clicks on the "Login" button 3. Guest user clicks on link "Register" 4. Website displays the registration form. 5. Guest user enter the following valid information: - UserName: Rose - FullName: Mrs.Rose - Password: Na1020@ - Re-Password: Na1020@ - Phone: 0123457854 - Gender: Female - Email: nn767898@gmail.com - Birthdate: 20/03/2025 6. Click "Register" button 7.Respond to login page. | User is successfully registered, redirected to the login page, and user details are stored in the database. | Server must be work Guest user is not logged in and wants to create an account. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Authent - 2] | Test registration with invalid email format - UserName: Rose - FullName: Mrs.Rose - Password: Na1020@ - Re-Password: Na1020@ - Phone: 0123457854 - Gender: Female - Email: test.com - Birthdate: 20/03/2025 | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Guest user clicks on the "Login" button 3. Guest user clicks on link "Register" 4. Website displays the registration form. 5. Guest user enter invalid email form (e.g., test.com). 6. Click "Register" button 7. Website displays an error message for invaild email format 8. Guest user corrects the mail format and resubmits the form. | Guest user is not logged in and wants to create an account. | Server must be work Guest user is not logged in and wants to create an account. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Authent - 3] | Test registration with invalid phone format - UserName: Rose - FullName: Mrs.Rose - Password: Na1020@ - Re-Password: Na1020@ - Phone: 03125 - Gender: Female - Email: nn767898@gmail.com - Birthdate: 20/03/2025 | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Guest user clicks on the "Login" button 3. Guest user clicks on link "Register" 4. Website displays the registration form. 5. Guest user enter invalid phone form (e.g., 03125). 6. Click "Register" button 7. Website displays an error message for correct phone format 8. Guest user corrects the mail format and resubmits the form. | Guest user is not logged in and wants to create an account. | Server must be work Guest user is not logged in and wants to create an account. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Authent - 4] | Test registration with Re-Password error - UserName: Rose - FullName: Mrs.Rose - Password: Na1020@ - Re-Password: Na1020 - Phone: 0123457854 - Gender: Female - Email: nn767898@gmail.com - Birthdate: 20/03/2025 | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Guest user clicks on the "Login" button 3. Guest user clicks on link "Register" 4. Website displays the registration form. 5. Guest user enter data error re-password 6. Click "Register" button 7. Website displays an error message for notification error 8. Guest user corrects the information and resubmits the form. | Guest user is not logged in and wants to create an account. | Server must be work Guest user is not logged in and wants to create an account. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Authent - 5] | Test registration with empty required fields - UserName - FullName - Password - Re-Password - Phone - Gender - Email - Birthdate | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Guest user clicks on the "Login" button 3. Guest user clicks on link "Register" 4. Website displays the registration form. 5. Guest user leaves - First Name: empty - Last Name: empty - Email: empty - Password: empty - Confirm Password: empty 6. Click "Register" button 7. Website displays an error message for invaild email format 8. Guest user corrects the mail format and resubmits the form. | System displays an error message for the empty fields and prevents registration until corrected. | Server must be work Guest user is not logged in and wants to create an account. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Authent - 6] | Test registration with password must be shorter than 6 characters, no uppercase letters | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Guest user clicks on the "Login" button 3. Guest user clicks on link "Don't have an account? Register" 4. Website displays the registration form. 5. 3. Guest user enters a Password shorter than 8 characters (e.g., pass12). 6. Click "Register" button 7. Website displays an error message indicating "Password must be at least 6 characters, including one uppercase letter and one lowercase letter' 8. Guest user corrects the Password and resubmits the form. | Displays an error message indicating "Password must be at least 6 characters, including one uppercase letter and one lowercase letter' | 1.Server must be work 2..Account must be in system | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Authent - 7] | Test registration with invalid birthdate ( date in the future) - UserName: Rose - FullName: Mrs.Rose - Password: Na1020@ - Re-Password: Na1020@ - Phone: 03125 - Gender: Female - Email: nn767898@gmail.com - Birthdate: 20/03/2026 | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Guest user clicks on the "Login" button 3. Guest user clicks on link "Don't have an account? Register" 4. Website displays the registration form. 5. 3. Guest user enters a date time in the future. 6. Click "Register" button 7. Website displays an error message. 8. Guest user corrects the birthdate and resubmits the form. | Displays an error message. | 1.Server must be work 2..Account must be in system | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Login by account
[Authent - 8] | View "Login" form | 1. Enter "homepage" to go to website | Location in the right corner of the screen: - Click on "Login" button - Show "Login" view form | 1.Server must be work 2..Account must be in system | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Authent - 9] | Check if the user can successfully log in with a valid username and password. | 1. Enter "homepage" to go to website | Redirect to home page. | 1.Server must be work 2..Account must be in system | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Authent - 10] | Check if the website handles an incorrect password. | 1. Enter "homepage" to go to website | System displays an error message "Username or password invalid!". | 1.Server must be work 2..Account must be in system | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Authent - 11] | Check if the website handles an userName unregistered | 1. Enter "homepage" to go to website | Displays an error message indicating "Username or password invalid!" | 1.Server must be work 2..Account must be in system | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Forgot Password
[Authent - 12] | Enter the correct email, username registered | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Guest user clicks on the "Login" button 3. Guest user clicks on link "Forgot Password" 4. Website displays the Forgot Password form. 5. 3. Guest user enters a email, userName registered. 6. Click "confirm" button 7. Website displays Reset Password. 8. Guest user enter the password and confirm-password and submits the form. 9. Send to login page | System update password successfull | 1.Server must be work 2..Account must be in system | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Authent - 13] | Enter non-existent email and username not match | 1. Enter "homepage" to go to website | Displays an error message indicating "Incorrect email or username. Please try again" | 1.Server must be work 2..Account must be in system | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Logout
[Authent - 14] | Check if the user can successfully log out from the website. | 1. Enter "homepage" to go to website 2. Guest user login with system. 3.Click the avatar icon in top-right of website. 4. Click "Logout" button | 1.User is logged out and redirected login page. No user-specific data is accessible until the user logs in again. | 1.Server must be work 2..Account must be in system | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Authent - 15] | Check if a logged-out user is restricted from accessing pages meant for logged-in users. | 1. Enter "homepage" to go to website 2. Guest user login with system. 3.Click the avatar icon in top-right of website. 4. Click "Logout" button 5.After logging out, try to directly access the restricted page by entering the URL in the browser (e.g, "order") | The system redirects the user to the loginpage when they try to access the restricted page. | 1.Server must be work 2..Account must be in system | Failed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Profile
[Authent - 16] | View profile | 1. Enter "homepage" to go to website 2. Guest user login with system. 3.Click "Profile" in top-menu of website. 4. System display user profile | The system displays user information accurately. | 1.Server must be work 2..Account must be in system | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Authent - 17] | Test change image avatar | 1. Enter "homepage" to go to website 2. Guest user login with system. 3.Click "Profile" in top-menu of website. 4. Click icon edit in below avatar. 5. Select file image then enter. 6. System save avatar in database. | System save informaton change in database. | 1.Server must be work 2..Account must be in system | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Authent - 18] | Edit profile with valid data: - Full name: Nguyen Hong Nhung - Gender: Female - Email address: nhungnhhe181566@fpt.edu.vn - Phone: 0123453642 - Birthdate: 28/03/2004 | 1. Enter "homepage" to go to website 2. Guest user login with system. 3.Click "Profile" in top-menu of website. 4. Click "Edit profile" 5. Enter valid data and submit 6. System update data in database. | System save informaton change in database. | 1.Server must be work 2..Account must be in system | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Authent - 19] | Edit profile with duplicate email: - Email address: nhungnhhe181566@fpt.edu.vn (existed in database) | 1. Enter "homepage" to go to website 2. Guest user login with system. 3.Click "Profile" in top-menu of website. 4. Click "Edit profile" 5. Enter duplicated email and submit 6. System display error "Update fail" | System display error message. | 1.Server must be work 2..Account must be in system | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Authent - 20] | Edit profile with duplicate phone: - Phone: 0123456789 (existed in database) | 1. Enter "homepage" to go to website 2. Guest user login with system. 3.Click "Profile" in top-menu of website. 4. Click "Edit profile" 5. Enter duplicated phone and submit 6. System display error "Update fail" | System display error message. | 1.Server must be work 2..Account must be in system | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Change password
[Authent - 21] | View change passwod page | 1. Enter "homepage" to go to website 2. Guest user login with system. 3.Click "Profile" in top-menu of website. 4. Click "Security" in the menu. 5. Observe change password screen. | System display screen. | 1.Server must be work 2..Account must be in system | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Authent - 22] | Test change pass with valid old password | 1. Enter "homepage" to go to website 2. Guest user login with system. 3.Click "Profile" in top-menu of website. 4. Click "Security" in the menu. 5. Enter correct old password. 6. Enter new pass and confirm new pass valid constrait pass and submit. 7. System save new password in database and display success message. | System display "Change password successfully!" and save new pass in database. | 1.Server must be work 2..Account must be in system | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Authent - 22] | Test change pass with invalid old password | 1. Enter "homepage" to go to website 2. Guest user login with system. 3.Click "Profile" in top-menu of website. 4. Click "Security" in the menu. 5. Enter incorrect old password. 6. Enter new pass and confirm new pass valid constrait pass and submit. 7. System display error message. | System display "Old password is incorrect!" and unsave new pass in database. | 1.Server must be work 2..Account must be in system | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Authent - 23] | The new password is in the incorrect format. - New password: Na102 | 1. Enter "homepage" to go to website 2. Guest user login with system. 3.Click "Profile" in top-menu of website. 4. Click "Security" in the menu. 5. Enter correct old password. 6. Enter new pass invalid format and submit. 7. System display error message. | System display "Mật khẩu phải dài ít nhất 8 ký tự và bao gồm chữ hoa, chữ thường, số và ký tự đặc biệt." | 1.Server must be work 2..Account must be in system | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH

## Defect log
Bug list
Defect ID | Module | Description | Type | Severity | Priority | Status | Created Date
DF-1 | Logout | When logged out of some admin pages, staff are not protected, can still access | User Interface Security | High | High | Fixed | 2025-03-27
DF-2 | Edit category | When editing categories, duplicate content is allowed between different categories | Bussiness rule | High | High | Fixed | 2025-03-27
DF-3 | Edit Brand | Unable to save information when editing, always reports an error "Invalid image URL! Please enter a valid path." | Functionality | High | High | Pending | 2025-03-27
DF-4 | Delete Brand | Unable to delete brands that are connected to the product | Functionality | High | High | Pending | 2025-03-27
DF-5 | Add Brand | Incorrect image link, unable to upload image | Functionality | High | High | Pending | 2025-03-27
DF-7
DF-8
DF-9
DF-10
DF-11
DF-12
DF-13
DF-14
DF-15
DF-16
DF-17
DF-18
DF-19
DF-20

## Main flow of Admin Management
Feature | Admin Management | [13 empty] | Passed
Test requirement | Check the functionalities of Admin role work well | [13 empty] | Failed
Number of TCs | 22 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 22 | 0 | 0 | 0
Round 2 | 22 | 0 | 0 | 0
Round 3 | 22 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Dashboard
[Admin - 1] | View dashboard | 1. Enter "homepage" to go to website 2. Login the system with Admin role. | The system displays the "Dashboard " | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Manage User
[Admin - 8] | Verify Display of User List | 1. Enter "homepage" to go to website 2. Login the system with Admin role. 3. Click "manage User" in left page. 4. View list user. | The system displays a table of users with actual data in system. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Admin - 9] | Check if the admin can change the user's status (Active/Inactive). | 1. Enter "homepage" to go to website 2. Login the system with Admin role. 3. Click "manage User" in left page. 4. Click "Inactive" to change the account to "Active" and vice versa. | The system displays notification and update data change. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Admin - 10] | Check if the admin can change a user's role (e.g., from Customer to Staff).. | 1. Enter "homepage" to go to website 2. Login the system with Admin role. | The system displays message "Update role successfully!!" | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Revenue
[Admin - 11] | View revenue management page | 1. Enter "homepage" to go to website 2. Login the system with Admin role. 3. Enter "Admin icon" to go to the management page 4.Click on "Order" and select "Revenue Management" | The system displays "Revenue Management" | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | KhoiNTA | Passed | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA
[Admin - 12] | Verify that the date filter works correctly | 1. Enter "homepage" to go to website 2. Login the system with Admin role. 3. Enter "admin icon" to go to the management page 4.Click on "Order" and select "Revenue Management" 5. Select a valid time period for statistics 6. Click "statistics" | The system displays the correct statistical data for the selected period | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | KhoiNTA | Passed | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA
[Admin - 13] | Verify that order information per user is displayed correctly | 1. Enter "homepage" to go to website 2. Login the system with Admin role. 3. Enter "Admin icon" to go to the management page 4.Click on "Order" and select "Revenue Management" | The table correctly displays the list of users, total successful orders, and total order amount per user | 1. Server must be work 2. User has logged in as a account before. 3. There are orders within the selected date range | Passed | 03/24 | KhoiNTA | Passed | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA
[Admin - 14] | Verify that the order quantity chart displays correctly | 1. Enter ""homepage"" to go to website 2. Login the system with Admin role. 3. Enter ""Admin icon"" to go to the management page 4.Click on ""Order"" and select ""Revenue Management""" 5.Click on "Order statistics" | The order quantity chart correctly represents different order statuses (Canceled, Successful, In transit, New Order) | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | KhoiNTA | Passed | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA
[Admin - 15] | Verify that the revenue chart works correctly | 1. Enter ""homepage"" to go to website 2. Login the system with Admin role. 3. Enter ""Admin icon"" to go to the management page 4.Click on ""Order"" and select ""Revenue Management""" 5.Click on "Revenue statistics" | The revenue chart accurately represents the revenue per day within the selected period | 1. Server must be work 2. User has logged in as a account before. 3.There are valid orders with revenue within the selected date range | Passed | 03/24 | KhoiNTA | Passed | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA
[Admin - 16] | Verify that the "Statistics" button functions correctly | 1. Enter "homepage" to go to website 2. Login the system with Admin role. 3. Enter "admin icon" to go to the management page 4.Click on "Order" and select "Revenue Management" 5. Select a valid time period for statistics 6. Click "statistics" | The system reloads and displays the correct statistical data | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | KhoiNTA | Passed | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA
[Admin - 17] | Validate without date entered | 1. Enter "homepage" to go to website 2. Login the system with Admin role. 3. Enter "admin icon" to go to the management page 4.Click on "Order" and select "Revenue Management" 5. No date entered 6. Click "statistics" | The system requires entering the date and month if you want to view statistics. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | KhoiNTA | Passed | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA
[Admin - 18] | Validate if entering a time in the future | 1. Enter "homepage" to go to website 2. Login the system with Admin role. 3. Enter "admin icon" to go to the management page 4.Click on "Order" and select "Revenue Management" 5. Select a valid time period for statistics 6. Click "statistics" | The system displays a message "Do not enter more than 1 day after the current date" | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | KhoiNTA | Passed | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA
Manage top best seller
[Admin - 19] | Verify that the product filter page displays correctly | 1. Enter "homepage" to go to website 2. Login the system with Admin role. 3. Enter "admin icon" to go to the management page 4.Click on "Top 10 Best Seller" | The page displays all filter fields and the best-selling product list table | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | KhoiNTA | Passed | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA
[Admin - 20] | Verify that filtering by keyword works correctly | 1. Go to "homepage" to enter the website 2. Log in to the system as Admin. 3. Go to "admin icon" to enter the management page 4.Click on "Top 10 Best Seller" 5. In the "Keyword" section, enter the appropriate keyword (ex: "Găng tay"...) | The product list updates to display only matching products | 1. Server must be work 2. User has logged in as a account before. 3.The database contains products matching the keyword | Passed | 03/24 | KhoiNTA | Passed | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA
[Admin - 21] | Verify that order information per user is displayed correctly | 1. Enter "homepage" to go to website 2. Login the system with Admin role. 3. Enter ""admin icon"" to go to the management page 4.Click on ""Top 10 Best Seller""" 5. Enter the information you want to check 6. Click "filter products" | The table correctly displays the list of users, total successful orders, and total order amount per user | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | KhoiNTA | Passed | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA
[Admin - 22] | Verify system behavior when no data is entered | 1. Enter "homepage" to go to website 2. Login the system with Admin role. 3. Enter ""admin icon"" to go to the management page 4.Click on ""Top 10 Best Seller""" 5. In the "Top selling products" section, delete the unit automatically. 6. Click "filter products" | The system automatically lists the 10 best-selling products compared to all products. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | KhoiNTA | Passed | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA
[Admin - 23] | Verify that filtering by price range works correctly | 1. Enter "homepage" to go to website 2. Login the system with Admin role. 3. Enter ""admin icon"" to go to the management page 4.Click on ""Top 10 Best Seller""" 5. In the product filter, enter the price range you want to filter. 6. Click "filter products" | The product list updates to show only products within the selected price range | 1. Server must be work 2. User has logged in as a account before. 3.The database contains products within the selected price range | Passed | 03/24 | KhoiNTA | Passed | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA
[Admin - 24] | Verify that filtering by category works correctly | 1. Enter "homepage" to go to website 2. Login the system with Admin role. 3. Enter ""admin icon"" to go to the management page 4.Click on ""Top 10 Best Seller""" 5. In the product filter, select the category you want to filter 6. Click "filter products" | The product list updates to display only products from the selected category | 1. Server must be work 2. User has logged in as a account before. 3.The database contains products within the selected price range | Passed | 03/24 | KhoiNTA | Passed | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA
[Admin - 25] | Verify that filtering by brand works correctly | 1. Enter "homepage" to go to website 2. Login the system with Admin role. 3. Enter ""admin icon"" to go to the management page 4.Click on ""Top 10 Best Seller""" 5. In the product filter, select the Brand you want to filter. 6. Click "filter products" | The product list updates to display only products of the selected brand | 1. Server must be work 2. User has logged in as a account before. 3.The database contains products within the selected price range | Passed | 03/24 | KhoiNTA | Passed | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA
[Admin - 26] | Verify that filtering by discount percentage works correctly | 1. Enter "homepage" to go to website 2. Login the system with Admin role. 3. Enter ""admin icon"" to go to the management page 4.Click on ""Top 10 Best Seller""" 5.In the product filter, select the discount you want to filter. 6. Click "filter products" | The product list updates to display only products with the selected discount percentage | 1. Server must be work 2. User has logged in as a account before. 3.The database contains products within the selected price range | Passed | 03/24 | KhoiNTA | Passed | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA
[Admin - 27] | Verify that filtering by size works correctly | 1. Enter "homepage" to go to website 2. Login the system with Admin role. 3. Enter ""admin icon"" to go to the management page 4.Click on ""Top 10 Best Seller""" 5. In the product filter, enter the size you want to filter 6. Click "filter products" | The product list updates to display only products available in the selected size | 1. Server must be work 2. User has logged in as a account before. 3.The database contains products within the selected price range | Passed | 03/24 | KhoiNTA | Passed | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA
[Admin - 28] | Verify that sorting by the number of best-selling products works correctly | 1. Enter "homepage" to go to website 2. Login the system with Admin role. 3. Enter ""admin icon"" to go to the management page 4.Click on ""Top 10 Best Seller""" 5. In the product filter, Enter a number in the "Top selling products" field. 6. Click "filter products" | The product list updates to display the top-selling products based on the selected number | 1. Server must be work 2. User has logged in as a account before. 3.The database contains products within the selected price range |  | 03/24 | KhoiNTA |  | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA
[Admin - 29] | Verify that the filter works correctly when selecting and filling from 1 item to filling all items | 1. Enter "homepage" to go to website 2. Login the system with Admin role. 3. Enter ""admin icon"" to go to the management page 4.Click on ""Top 10 Best Seller""" 5. In the "Top selling products" section, select the products you want to find. 6. Click "filter products" | The system automatically lists accurate information with the filter options. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | KhoiNTA | Passed | 03/25 | KhoiNTA | Passed | 03/26 | KhoiNTA

## Main flow of Staff Managemen
Feature | Main flow of Staff Management | [13 empty] | Passed
Test requirement | [14 empty] | Failed
Number of TCs | 41 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 37 | 4 | 0 | 0
Round 2 | 39 | 2 | 0 | 0
Round 3 | 40 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
View Dashboard
Staff-1 |  | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3.Click "Dashboard" on the left menu. 4. Observe the "" statistic | The "Total Classes" count matches the actual number of classes the student is enrolled in. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-2 |  | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3.Click "Dashboard" on the left menu. 4. Observe the "" statistic | The pie chart accurately represents the distribution of class types. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-3 |  | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3.Click "Dashboard" on the left menu. 4. Observe the "" statistic | The system displays the total numbers for "Submitted," "Saved Drafts," "Graded," and "Ungraded," along with two charts: "Weekly Writing Performance" and "Submission." | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Manage product
Staff-4 | View list product | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3.Click "Prodcut" on the left menu. 4. Observe the "Product list" screen | System display "View Poduct"for staff page | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
| Search with valid query | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3.Click "Prodcut" on the left menu. 4. User enter a vaild search (e.g., "Găng"). 5. System displays a list of Product with product name contain "Găng" | The system displays the all product list with product name contains text search | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-6 | Search with no results | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3.Click "Prodcut" on the left menu. 4. User enter a vaild search without no result (e.g., "absxd"). 5. System displays a list of Product empty | The system displays the empty product list | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-7 | Search with empty query | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3.Click "Prodcut" on the left menu. 4. User enter a empty query search (e.g., ""). 5. System displays all Product. | The system displays the all product list | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-8 | Filter with all query: - Danh mục: Găng tay - Thương hiệu: Nike - Trạng thái: Active - Khoảng giá: 1370000 | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3.Click "Prodcut" on the left menu. 4. User enter all query filter valid 5. System displays the list Product fit with filter conditions. | The system displays the list Product fit with filter conditions | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-9 | Add product successful - Product name: "Găng tay hạng cao cấp" - Image: "product_image.jpg" - Description: "Sản phẩm găng tay thượng hạng" - Category: "Găng tay" - Price: "500000" - Brand: "Nike" - Unit of sold: "0" - Supplier: "Nike VietNam" - Discount: "5" - Rating: "1" - Status: "Còn hàng" - Unit in stock: "100" - Size: "M" | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Prodcut" on the left menu. 4. Click "Thêm sản phẩm" on the above. 5. Enter the valid information. 6. Click "Thêm sản phẩm" 7. View list product after add product successful. | The system displays a list of all products that must contain the product that was just successfully added. Product saved successfully to database. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-10 | Add product with empty - Product name: "" - Image: "" - Description: "" - Category: "" - Price: "" - Brand: "" - Unit of sold: "" - Supplier: "" - Discount: "" - Rating: "" - Status: " - Unit in stock: "" - Size: "" | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Prodcut" on the left menu. 4. Click "Thêm sản phẩm" on the above. 5. Enter the empty value. 6. Click "Thêm sản phẩm" 7. System display error message, enter valid data and resubmit. | Cannot add product when one of the information fields is blank | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-11 | View detail product | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Prodcut" on the left menu. 4. Click "Chi tiết" on the right for each product. 5. System display product information detail. | The system display product information detail. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-12 | Test function Inactive/Active product | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Prodcut" on the left menu. 4. Click "Active/Inactive" on the right for each product. 5. The system confirms the information 6. If you agree, the system will Active/Inactive the selected product. | The product is transformed into the desired state. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Manage feedback
Staff-13 | View list feedback | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3.Click "Feedback" on the left menu. 4. Observe the "Feedback list" screen | System display "View Feedback"for staff page | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-14 | Test function Delete parent feedback | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Feedback" on the left menu. 4. Click "Xóa" on the right for each parent feedback. 5. The system confirms the your action 6.If you agree, the system will delete the selected response and its child responses. | Feedback will be deleted in database. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-15 | Test function Delete child feedback | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Feedback" on the left menu. 4. Click "Xóa" on the right for each child feedback. 5. The system confirms the your action 6.If you agree, the system will only delete the selected feedback. | Feedback will be deleted in database. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-16 | Test function reply parent feedback | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Feedback" on the left menu. 4. Click "Trả lời" on the right for each parent feedback. 5. The system display box. 6. Enter the feedback and click "Gửi phản hổi" 7. Child response will be generated. | The system saves changes to the database. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Manage coupon
Staff-17 | View list coupon | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Coupon" on the left menu. 4. Observe the "Coupon list" screen | System display list coupon | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-18 | Search coupon | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Coupon" on the left menu. 4. Enter search text Code coupon. | The system displays a list of coupons containing the search text. |  | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-19 | Filter coupon by status | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Coupon" on the left menu. 4. Select status "Active" or "Inactive" in dropdown to filter. | The system displays a list of coupons by status. |  | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-20 | Change status coupon | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Coupon" on the left menu. 4. Click the "Active" button to switch to "Inactive" state and vice versa. | The system saves the changed information into the database. |  | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-21 | Edit coupon with valid data | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Coupon" on the left menu. 4. Click the "Edit". 5. Enter valid data and save | The system saves the changed information into the database and display "Cập nhật mã giảm giá thành công!" . |  | Passed | 03/24 | NhungNH | Passed | 10/15 | NhungNH | Passed | 03/26 | NhungNH
Staff-22 | Edit coupon with valid data: - Start date: 01/06/2025 - End date: 01/1/2025 | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Coupon" on the left menu. 4. Click the "Edit". 5. Enter invalid data start date > end date and save. | The system don't saves the changed information into the database and display error mesage |  | Failed | 03/24 | NhungNH | Passed | 10/15 | NhungNH | Passed | 03/26 | NhungNH
Staff-23 | Add coupon with valid data: - Code: "TESTCOUPON" - Discount: 5 - Start date: "01/01/2025" - End date: "01/12/2025" - Giá trị đơn hàng tối thiểu: 150000 - Giá trị giảm giá tối đa: 10000 - Mô tả: "Test thử nghiệm coupon" - Điểm tối thiểu: 0 - Lượt sử dụng tối đa: 100 | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Coupon" on the left menu. 4. Click the "Thêm mã giảm giá". 5. Enter valid data and save. | The system saves the changed information into the database and display "Thêm mã giảm giá thành công!". System send email to users with satisfied userpoint. |  | Passed | 03/24 | NhungNH | Passed | 10/15 | NhungNH | Passed | 03/26 | NhungNH
Staff-24 | Add coupon with duplicate code coupon: - Code: "TESTCOUPON" - Discount: 5 - Start date: "01/01/2025" - End date: "01/12/2025" - Giá trị đơn hàng tối thiểu: 150000 - Giá trị giảm giá tối đa: 10000 - Mô tả: "Test thử nghiệm coupon" - Điểm tối thiểu: 0 - Lượt sử dụng tối đa: 100 | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Coupon" on the left menu. 4. Click the "Thêm mã giảm giá". 5. Enter daplucate code coupon and save. | The system display "Thêm thất bại. Vui lòng thử lại". |  | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Manage category
Staff-25 | View list category | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Category" on the left menu. 4. Observe the "Category list" screen | System display list Category |  | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-26 | Search category | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Category" on the left menu. 4. Enter search text category name. | The system displays a list of Category containing the search text. |  | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-27 | Sort category | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Category" on the left menu. 4. Select type for sort category from dropdown. | The system displays a list of Category order. |  | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-28 | Add valid category: - Category name: "Găng tay cao cấp" - Description: "nên mua" - Parent category: "Găng tay" | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Category" on the left menu. 4. Click the "Add category". 5. Enter valid data and save. | The system saves the changed information into the database and display "Category add successful!". |  | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-29 | Add exist category: - Category name: "Găng tay cao cấp" - Description: "nên mua" - Parent category: "Găng tay" | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Category" on the left menu. 4. Click the "Add category". 5. Enter duplicate data and save. | The system display error message "Category already exists". |  | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-30 | Edit category: - Category name: "Găng tay xịn" - Description: "nên mua" - Parent category: "Găng tay" | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Category" on the left menu. 4. Click the "edit category". 5. Enter data and save. | The system saves the changed information into the database and display "Category update successful!". |  | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-31 | Edit category with category name exist: - Category name: "Găng tay cao cấp" - Description: "nên mua" - Parent category: "Găng tay" | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Category" on the left menu. 4. Click the "Edit". 5. Enter data exits and save. | The system display error message "Category already exists with identical information!". |  | Failed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Manage Brand
Staff-32 | View list Brand | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Brand" on the left menu. 4. Observe the "Brand list" screen | System display list Brand |  | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-33 | Edit brand | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "brand" on the left menu. 4. Click "Sửa". 5. Enter data valid. | The system saves the changed information into the database. |  | Failed | 03/24 | NhungNH | Failed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-35 | Add brand | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "brand" on the left menu. 4. Click "Thêm thương hiệu". 5. Enter valid data | The system save brand to database |  | Failed | 03/24 | NhungNH | Failed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Manage Order
Staff-36 | View "Thống kê doanh thu" with valid input: - From date: "23/03/2025" - End Date: " 29/03/2025" | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Order" on the left menu. 4. Click "Quản lý bán hàng" 5. Enter From date <= end date | The system display respone data revevue. |  | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-37 | View "Thống kê doanh thu" with invalid input: - From date: "30/03/2025" - End Date: " 29/03/2025" | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Order" on the left menu. 4. Click "Quản lý bán hàng" 5. Enter From date > end date | The system display error message "Ngày bắt đầu không được lớn hơn ngày kết thúc." |  | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-38 | View "Thống kê doanh thu" with invalid input: - From date: "30/03/2025" - End Date: " 29/03/2025" | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Order" on the left menu. 4. Click "Quản lý bán hàng" 5. Enter From date > Today | The system display error message "Ngày không được vượt quá ngày hiện tại cộng 1 ngày." |  | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-39 | View "Danh sách đơn hàng" with invalid input: | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Order" on the left menu. 4. Click "Danh sách đơn hàng" 5. View order list sale | The system display list order sale |  | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-40 | Update order status | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Order" on the left menu. 4. Click "Danh sách đơn hàng" 5. Update order status | The system saves the order status successfully updated and notifies |  | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-41 | Search order by code oreder and filter by status, date, sort | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Order" on the left menu. 4. Click "Danh sách đơn hàng" 5. Enter the code order to place input "Nhập mã đơn hàng.." , select other condition to filter and submit | The system displays orders that satisfy the conditions. |  | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Staff-42 | View order detail sale | 1. Enter "GoalZonepage" to go to website 2. Login the system with Staff role. 3. Click "Order" on the left menu. 4. Click "Danh sách đơn hàng" 5. Click into code order to view order detail of this order. | The system displays detailed order matching |  | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[send notification-4] | Verify input when user leaves blank "Content" | 1. Login in the system with Examiner role 2. Click on "Send Notification" tab in the left menu 3. Fill in : - Title - Content: empty | Show toast "Please enter both title and content" |  | Passed | 2024-08-08 | HoaNH | Passed | 2024-08-08 | HoaNH | Passed | 2024-08-08 | HoaNH

## Main flow of Customer Manageme
Feature | Customer | [13 empty] | Passed
Test requirement | Perform the functionalities of role Customer | [13 empty] | Failed
Number of TCs | 15 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 15 | 0 | 0 | 0
Round 2 | 15 | 0 | 0 | 0
Round 3 | 15 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Manage home
[Customer- 1] | View Products | 1. Access the homepage of the website. 2. Log in to the system with the Customer role. | The system displays the list of products. | 1. The server is running. 2. The user has an existing account and has logged in before. | Passed | 03/24 | AnhLH | Passed | 03/25 | AnhLH | Passed | 03/26 | AnhLH
[Customer- 2] | Ensure clicking the "CONTACT US" button leads to the contact page. | 1. Click on "CONTACT US" in the navigation bar. 2. Check if the system loads the Contact Us page. | The system redirects the user to the Contact Us page, displaying contact information and a form. | 1. The server must be running. 2. The homepage is accessible. | Passed | 03/24 | AnhLH | Passed | 03/25 | AnhLH | Passed | 03/26 | AnhLH
[Customer- 3] | Ensure clicking the profile icon leads to the user profile page or login screen. | 1. Click on the Profile icon (top right corner). 2. Customer profile page display system. | If logged in → The system navigates to the Profile page. If not logged in → The system displays the Login page. | 1. The server must be running. 2. The homepage is accessible. 3.The user must have a valid account | Passed | 03/24 | AnhLH | Passed | 03/25 | AnhLH | Passed | 03/26 | AnhLH
[Customer- 4] | Check if clicking the shopping cart icon redirects to the cart page. | 1. Click on the Shopping Cart icon (top right corner). 2. Observe the system response. | The system navigates to the Shopping Cart page and displays added products | 1. The server must be running. 2. The homepage is accessible. 3. The user must have added at least one product to the cart | Passed | 03/24 | AnhLH | Passed | 03/25 | AnhLH | Passed | 03/26 | AnhLH
Manage cart
[Customer- 4] | View cart with list cart not empty | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Login with role customer. 3. Click "Cart icon". 4. Vieew cart list | System display list product in cart. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Customer- 4] | Decrease/Increase quantity of products in cart | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Login with role customer. 3. Click "Cart icon". 4. Decrease/Increase quantity of products in cart and submit | Cart quantity change in system | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Customer- 4] | Deleted product from cart | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Login with role customer. 3. Click "Cart icon". 4. Click "Xóa" in right product. | Cart quantity change in system | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Manage my order
[Customer- 4] | View list order history | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Login with role customer. 3. Click "Icon avatar" and choose "My order". 4. View list order history by status order. | The system displays accurate order information according to the current status. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Customer- 4] | Cancle order | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Login with role customer. 3. Click "Icon avatar" and choose "My order". 4. Choose status "Chờ xác nhận", if button "Cancle" exist, you can choose thís and confirm this action. | The system updated the status of that order as canceled. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Customer- 4] | View list order detail | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Login with role customer. 3. Click "Icon avatar" and choose "My order". 4. Choose one status (e.g, "Chờ xác nhận") 5. Click button "Xem" in the right of order. 6. View order detail. | The system displays detailed order information exactly as saved in the system. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Customer- 4] | repurchase product | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Login with role customer. 3. Click "Icon avatar" and choose "My order". 4. Choose one status (e.g, "Chờ xác nhận") 5. Click button "Xem" in the right of order. 6. View order detail and click "Mua lại". | The product will be added to the cart. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
Order process
[Customer- 4] | Add coupon: - Coupon code: "FLASHSALE: | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Login with role customer. 3. Click "Cart icon". 4. Click "check out" in bottom of page. 5. Enter code coupon correct and click "Áp dụng". | System display success message and discount on purchase with coupon code | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Customer- 4] | Add address with valid data | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Login with role customer. 3. Click "Cart icon". 4. Click "check out" in bottom of page. 5. Click "Add address". 6. Enter data valid from addressbox and submit. | System save address to database. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Customer- 4] | Choose payment method | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Login with role customer. 3. Click "Cart icon". 4. Click "check out" in bottom of page. 5. Enter correct order data shpping. 6. Click "Đặt hàng". 7. Choose payment method (e.g, COD) and submit. 8. The system sends notifications to the home page.. | Order payment status information will be updated and saved in the system. | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH
[Customer- 4] | Add feedbackadd feedback when purchased | 1. Enter "homepage" to go to website Location in the right corner of the screen: 2.Login with role customer. 3. Click "Icon avatar" and choose "My order". 4. Choose one status (e.g, "Chờ xác nhận") 5. Click button "Xem" in the right of order. 6. View order detail and click "Đánh giá". 7. Click "Viết đánh giá" and input feedback in feedback box in product detail page. | System to update and record assessment information | 1. Server must be work 2. User has logged in as a account before. | Passed | 03/24 | NhungNH | Passed | 03/25 | NhungNH | Passed | 03/26 | NhungNH